## Sheet1
Sprint Start Date | 2019-08-19 | Day of the Sprint | Forecast | Target | Actual
Sprint End Date | 2019-08-25 | 0 | 19.6 | 28 | 21
Working Days | 7 | 1 | 16.8 | 24 | 16
Work Hours Per Day | 4 | 2 | 14 | 20 | 12
Total Available Hours | 28 | 3 | 11.2 | 16 | 10
Average Daily Available Hours | 4 | 4 | 8.4 | 12 | 6
Average Productivity% | 70 | 5 | 5.6 | 8 | 5
Productive Hours | 19.6 | 6 | 2.8 | 4 | 2
Average Daily Productive Hours | 2.8 | 7 | 0 | 0 | 0