## Sheet1
Sprint Start Date | 2019-08-26 | Day of the Sprint | Forecast | Target | Actual
Sprint End Date | 2019-09-01 | 0 | 16.8 | 21 | 16
Working Days | 7 | 1 | 14.4 | 18 | 14
Work Hours Per Day | 3 | 2 | 12 | 15 | 12
Total Available Hours | 21 | 3 | 9.6 | 12 | 9
Average Daily Available Hours | 3 | 4 | 7.2 | 9 | 6
Average Productivity% | 80 | 5 | 4.8 | 6 | 5
Productive Hours | 16.8 | 6 | 2.4 | 3 | 4
Average Daily Productive Hours | 2.4 | 7 | 0 | 0 | 0