## Sheet1
Sprint Start Date | 2019-08-19 | Day of the Sprint | Estimated | Target | Actual
Sprint End Date | 2019-08-25 | 1 | 4.8 | 6
Working Days | 7 | 2 | 4 | 5
Work Hours Per Day | 1 | 3 | 3.2 | 4
Total Available Hours | 7 | 4 | 2.4 | 3 | 3
Average Daily Available Hours | 1 | 5 | 1.6 | 2 | 2
Average Productivity% | 80 | 6 | 0.8 | 1 | 1
Productive Hours | 5.6 | 7 | 0 | 0 | 0
Average Daily Productive Hours | 0.8