## Sheet1
Sprint Start Date | 2019-08-26 | Day of the Sprint | Forecast | Target | Actual
Sprint End Date | 2019-09-01 | 1 | 9.6 | 12
Working Days | 7 | 2 | 8 | 10
Work Hours Per Day | 2 | 3 | 6.4 | 8
Total Available Hours | 14 | 4 | 4.8 | 6
Average Daily Available Hours | 2 | 5 | 3.2 | 4
Average Productivity% | 80 | 6 | 1.6 | 2
Productive Hours | 11.2 | 7 | 0 | 0
Average Daily Productive Hours | 1.6