## Sheet1
Sprint Start Date | 2019-09-02 | Day of the Sprint | Estimated | Target | Actual
Sprint End Date | 2019-09-08 | 1 | 9.6 | 12 | 11
Working Days | 7 | 2 | 8 | 10 | 8
Work Hours Per Day | 2 | 3 | 6.4 | 8 | 8
Total Available Hours | 14 | 4 | 4.8 | 6 | 4
Average Daily Available Hours | 2 | 5 | 3.2 | 4 | 1
Average Productivity% | 80 | 6 | 1.6 | 2 | 0
Productive Hours | 11.2 | 7 | 0 | 0 | 0
Average Daily Productive Hours | 1.6