## Sheet1
Sprint Start Date | 2019-09-09 | Day of the Sprint | Estimate | Target | Actual
Sprint End Date | 2019-09-13 | 1 | 6.4 | 8 | 8
Working Days | 5 | 2 | 4.8 | 6 | 5
Work Hours Per Day | 2 | 3 | 3.2 | 4 | 5
Total Available Hours | 10 | 4 | 1.6 | 2 | 5
Average Daily Available Hours | 2 | 5 | 0 | 0 | 5
Average Productivity% | 80
Productive Hours | 8
Average Daily Productive Hours | 1.6